**Sprint 2**

Total Story Points: **32** Total Hours: **202**

Current Velocity: ***undefined***

**S09: Extend City Information**

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
| T50 | Button (viewable only by admins) to create new item types | 4 |  |
| T51 | Form for entering item attributes and details | 8 |  |
| T52 | New type is added to the database | 2 |  |
| T53 | Write test cases | 8 |  |
| T54 | Verify story is complete (acceptance test) | 2 |  |
|  | Story Points: **4** Total Hours: | **24** |  |

**S08: Multiple Cities**

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
| T55 | Option to choose from a list of cities from the menu button | 4 | 2 |
| T56 | Items displayed are only from the selected city | 8 | 7 |
| T57 | Jumps to a main page with the new set of information for the chosen city | 4 | 5 |
| T58 | Write test cases | 8 |  |
| T59 | Verify story is complete (acceptance test) | 4 |  |
|  | Story Points: **4** Total Hours: | **28** |  |

**S20: Individual Items page**

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
| T60 | Items direct to separate page when clicked | 4 |  |
| T61 | Separate page includes all available information for the item | 12 |  |
| T62 | Button to go back to item list | 8 |  |
| T63 | Write test cases | 8 |  |
| T64 | Verify story is complete (acceptance test) | 2 |  |
|  | Story Points: **8** Total Hours: | **34** |  |

**S16: Item search**

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
| T65 | Text box for search input on the main view page | 4 |  |
| T66 | Search can be executed with 'Enter' key after field input | 4 |  |
| T67 | List of results displayed after executing search | 10 |  |
| T68 | Write test cases | 8 |  |
| T69 | Verify story is complete (acceptance test) | 4 |  |
|  | Story Points: **4** Total Hours: | **30** |  |

**S17: Favourites**

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
| T70 | Favourite button on items | 4 |  |
| T71 | List with all favourites in main view | 10 |  |
| T72 | Unique favourite list for each account | 8 |  |
| T73 | Write test cases | 4 |  |
| T74 | Verify story is complete (acceptance test) | 4 |  |
|  | Story Points: **4** Total Hours: | **30** |  |

**S19: Sorting Items**

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
| T75 | At least an option to sort by name | 4 |  |
| T76 | Option to sort by one of: name, rating, price etc. | 8 |  |
| T77 | If the sorting filter is numeric, option to sort ascending or descending | 4 |  |
| T78 | Write test cases | 4 |  |
| T79 | Verify story is complete (acceptance test) | 4 |  |
|  | Story Points: **4** Total Hours: | **24** |  |

**S18: Reviews**

|  |  |  |  |
| --- | --- | --- | --- |
| Task ID | Task Description | Estimate | Taken |
| T80 | Form with review fields | 8 | 6 |
| T81 | Review form only appears when user is logged in | 2 | 1 |
| T82 | Feature to select star rating out of 5 | 4 | 6 |
| T83 | Submitted reviews appear on individual item pages | 8 | 6 |
| T84 | Write test cases | 4 |  |
| T85 | Verify story is complete (acceptance test) | 4 |  |
|  | Story Points: **4** Total Hours: | **30** |  |